## Sheet1
No. | Project Phase | Risk | Measures
1 | Resource Allocation Phase | Due to the large overall project budget, wide coverage, and the need for higher-level approval processes, there may be unexpected resource allocation processes or prerequisites, causing the overall progress to be delayed. | Strengthen communication, anticipate changes in resource allocation requirements, and prepare the necessary documents. At the same time, expedite the process, follow up in parallel, and compress the internal process time within the technology department.
|  | Since the project involves Information Innovation resources, the process will escalate for approval, which may result in unexpected resource allocation processes or prerequisites, causing delays. | Strengthen communication, anticipate changes in resource allocation requirements, and prepare the necessary documents.
|  | Due to various factors, there may be delays in non-technology department processes. | Expedite the process, follow up in parallel, and compress the internal process time within the technology department.
2 | Evaluation and Procurement Phase | Without pre-qualification, there may be too many vendors purchasing the bid documents and actually participating in the evaluation, increasing the unpredictability of the actual evaluation time and quantity. | Clearly inform participating vendors about the functional/non-functional requirements of shortlisted products and the preparation requirements for evaluation tools, advising them to conduct a self-assessment. Schedule the evaluations properly, allowing for more flexibility, and actively engage in learning and communication with internal and external projects.
|  | During the actual evaluation, venue support is required, and preparation time may be long. | Estimate the availability of server rooms based on the evaluation schedule.
|  | The evaluation process is complex, and there may be on-site disputes. | Assign additional security and network professionals to participate in the on-site evaluation.
|  | The requirements are complex, and many technologies are still in development. Vendors need to adapt and interface, and some functions may not meet the requirements. | Strengthen communication to synchronize the latest requirements, and have vendors iteratively develop products to meet internal needs. Additionally, conduct product trials in a timely manner.
|  | SOC products require vendors to have high levels of experience and technical expertise, and there is no unified standard in the industry. If there is a significant difference between the procured products and the actual requirements, it may affect implementation and project progress. | To avoid malicious competition from smaller vendors, it is recommended to use an invitation-based procurement method. Additionally, plan for a period where both the new and old platforms run in parallel to ensure a smooth transition in functionality and strategy.
3 | Implementation Phase | Resources may not be available on time due to various constraints. | Strengthen internal and external communication to ensure resources are available on time.
|  | We have limited implementation experience. | Organize professionals to participate, and have vendors assign more personnel for support.
|  | The project needs to integrate with other platforms, and the scale of external systems varies, posing risks of interface issues during implementation. | Implement a security container deployment plan and an emergency response plan. Additionally, encourage vendors to invest more high-level technical support personnel.
|  | The scale of SOC construction is large, with many localized custom developments. We have a tight schedule and heavy tasks, which may lead to interface issues with existing systems and incomplete localization of custom functions. | Address this by modularizing the existing SOC self-developed platform to enhance reusability, and strengthening project scope and progress control to achieve agile iterations and fast delivery, ensuring on-time delivery.
4 | Operation Phase | There may be false positives in the rules. | Utilize the current gray verification environment to detect anomalies early. Continue to optimize security monitoring and rule adjustments.
|  | The platform itself may have system, application, or business vulnerabilities. | Regularly conduct vulnerability scans and penetration tests, track industry vulnerabilities in related components, and apply patches promptly.
|  | There may be system failures. | Fully implement high availability technologies, establish robust emergency plans, and aim to reduce failures to business jitter levels.
|  | There may be equipment failures. | Deploy in a bypass configuration under normal circumstances, and use serial traction in emergencies. Implement robust availability monitoring and regular inspections.